## README
VELOOP Rewards: Data Analyst Task 01
Deliverable | 19 Assumption & Verification Register (Work Package S) + Source & Verification Register (section 6)
Purpose | Every unknown recorded instead of guessed, and every important fact with its source.
Status | Proposed analytics specification. Nothing here is verified as implemented in VELOOP production.
Prepared | 2026-10-01
Sheets | Assumption_Register, Source_Register

## Assumption_Register
id | unknown | why_it_matters | source_checked | risk | verification | owner | status
A-001 | Does the backend or frontend currently emit ANY analytics events (task, reward, wallet, withdrawal)? | Every event in deliverable 08 is proposed until this is known. | Help center, brief | High | Engineering walkthrough of current logging | Engineering | To Be Verified
A-002 | Which features are live in production today (vs help-page only)? | Instrumentation priority and coverage matrix status. | Help center, homepage | High | Product owner confirms feature list | Product | To Be Verified
A-003 | Is user_id stable, opaque and never reused? What is its real format? | All joins depend on it. | Supplied data (simulated format only) | High | Inspect auth/account schema | Engineering | To Be Verified
A-004 | Timezone of stored timestamps (supplied data has none; assumed IST). | Daily KPIs shift by 5.5 h if wrong. | Supplied data; daily-reward page uses IST | High | Check DB column types and server TZ | Engineering | To Be Verified
A-005 | Is there a stored event_id / idempotency key on rewards and wallet writes? | Without it duplicate credits cannot be detected reliably. | None found | High | Engineering review of reward and wallet services | Engineering | To Be Verified
A-006 | Does a wallet ledger (one row per movement) exist, or only balances? | Wallet KPIs and reconciliation need a ledger. | Wallet help page mentions 'balance movement' | High | Inspect wallet tables | Engineering | To Be Verified
A-007 | Session definition and inactivity timeout. | Sessions, returning users, session duration. | None found | Medium | Agree definition (proposal: 30 min inactivity) | Engineering + Data | Proposed
A-008 | Can 'Pending Verification' users have sessions without a login record? | Explains DQ-C03 (72 users). | Supplied data | Medium | Product confirms rule | Product | To Be Verified
A-009 | Is email verification required for an account to be Active? | Explains DQ-C08 (42 users). | Supplied data | Low | Product confirms rule | Product | To Be Verified
A-010 | VE, Gem and Token conversion rates to INR, and their effective dates. | Reward liability in INR cannot be computed (K-RWD-02 INR). | Help center: rates 'set by the platform', not published | High | Finance provides rate table with history | Finance / Founder | To Be Verified
A-011 | Real withdrawal statuses and reason codes used by operations. | D2 lifecycle and K-WDR-04 categories are proposed. | Withdrawal help pages | High | Operations shares current workflow | Operations | To Be Verified
A-012 | Is XP stored in the wallet ledger or only on the profile? | Decides whether XP rows belong in wallet_transactions. | Currencies page: XP is progression | Medium | Engineering confirms | Engineering | Proposed (assumed: not in wallet)
A-013 | Abandonment timeout for a started task (how long before 'abandoned'). | K-ENG-05 depends on it. | None found | Medium | Product/engineering agree per task type | Product + Engineering | Proposed
A-014 | Which ad/survey/offer partners are used and what callbacks (postbacks) they send. | Third-party tracking reliability (C4). | Privacy policy names partner categories only | High | Engineering lists partners and callback fields | Engineering | To Be Verified
A-015 | Approved reason categories for reward reversal and withdrawal rejection. | Proposed categories may not match operations. | Help pages list reasons in prose | Medium | Operations + Trust & Safety review | Operations | Proposed
A-016 | When is a referral record created: at share, at link click, or at registration? | K-REF-01 meaning. | Referral page | Medium | Engineering confirms flow | Engineering | To Be Verified
A-017 | What counts as the 'first eligible activity' for referral activation? | K-REF-03 definition. | Referral page ('may need') | Medium | Product defines | Product | To Be Verified
A-018 | Is a mobile app live? Homepage says 'Get Soon The App'; supplied platform is 100% Web. | Platform dimension and SDK choice. | Homepage, supplied data | Medium | Product confirms | Product | To Be Verified
A-019 | Is support handled in a ticketing tool or only by email? | Support KPIs need structured tickets. | Help center lists Gmail addresses | Medium | Operations confirms | Operations | To Be Verified
A-020 | What happens to a balance when a reward is reversed after the VEs were already withdrawn (negative balance allowed? debt? write-off?). | Ledger rules and reversal KPIs. Simulated data shows 5 users go negative (check S08). | Gems/currency pages mention reversal and forfeit, not negative balances | High | Finance + Product policy | Finance / Product | To Be Verified
A-021 | Homepage figures (1,570,253+ users, 1,500,470+ paid out): source and definition. | Must not be used as metrics; conflict with the brief. | Homepage | High | Founder confirms whether these are real, demo or placeholder | Founder | To Be Verified
A-022 | Crypto wallet payouts and 'Staking' link on homepage vs UPI/PayPal/gift cards on help center. | Payout method allowed values. | Homepage vs withdrawal page | Medium | Founder confirms current payout methods | Founder | To Be Verified
A-023 | Reference date and logic used to derive is_active_7d/30d and days_since_registration in the supplied data (inferred 2026-09-15 00:00, login-based). | Reproducibility of activity flags. | Supplied data (reverse-engineered) | Low | Dataset owner confirms | Dataset owner | Proposed
A-024 | Data retention period for raw events and personal data. | Storage design and privacy. | Privacy policy: 'as long as reasonably necessary' | Medium | Legal/founder sets periods | Founder / Legal | To Be Verified
A-025 | Which analytics/BI tools VELOOP already uses (if any). | Pipeline proposal should reuse existing tools. | Privacy policy mentions analytics tools generically | Medium | Engineering lists current stack | Engineering | To Be Verified
A-026 | Is promo-code text sensitive (shared publicly) or single-use secrets? | Whether promo_code_id is enough. | Promo code page | Low | Product confirms | Product | Proposed
A-027 | Which email address is the official channel for this assignment (velooprewardsofficial@ vs velooprewardsteam@)? | Correct submission/support channel. | Email vs help center | Low | Ask in reply email | Intern | To Be Verified

## Source_Register
source_id | information | source | source_type | date_checked | status | notes
SRC-01 | Task brief: deliverables, rules, minimum events, KPI areas, dataset expectations. | Data_Analyst_01.pdf (VELOOP Rewards, Task 01) | Internal | 2026-10-01 | Confirmed | Sections 1, 3 and 4 are missing from the PDF (numbering jumps 2 -> 5). No explicit calendar deadline in the PDF; duration stated as 22-24 days and 22-25 days in two places.
SRC-02 | Assignment email: GitHub repo + README, deploy on Vercel/Netlify, submit both links. | Email from VELOOP Rewards (Ayan Alam), 12:46 PM | Internal | 2026-10-01 | Confirmed | Email is addressed to 'Anurag'. Support email given as velooprewardsofficial@gmail.com, which differs from the help-center address (SRC-12).
SRC-03 | Supplied dataset: Users_1000_Clean (1,000 x 27), Users_Messy_Audit (1,008 x 28), Data_Dictionary (25 fields), Synthetic_Summary, README_Data_Status. | VELoop_Rewards_Data_01.xlsx (Google Drive folder in brief) | Simulated | 2026-10-01 | Confirmed | Only Users data supplied. Task Activity, Rewards, Wallet, Withdrawals, Referrals, Feature Events and Messy Data sheets expected by the brief are absent.
SRC-04 | Platform currencies: VEs (main reward credits), XP (progression), Gems (exchangeable), Tokens (selected purchases/actions), Spins (wheel). Virtual credits, not bank balances. | https://www.velooprewards.in/help-center/getting-started/platform-currencies | Official | 2026-10-01 | Confirmed | Published policy. Conversion rates not published.
SRC-05 | Withdrawals: minimum Rs. 10; methods UPI, PayPal, Amazon Gift Cards, Google Play Gift Cards; usually within 24 h, up to 72 h in review cases. | https://www.velooprewards.in/help-center/withdrawals/how-withdrawals-work | Official | 2026-10-01 | Confirmed | Last updated May 23, 2026. Methods 'may vary based on user eligibility, region, payout partner support'.
SRC-06 | Reward verification is 'manual and system-based'; rewards/withdrawals may be delayed, rejected or reversed; may apply before or after a reward is granted. | https://www.velooprewards.in/help-center/withdrawals/reward-verification | Official | 2026-10-01 | Confirmed | No thresholds published; none are invented here (integrity rule 4).
SRC-07 | Watch Ads: rewards depend on partner tracking; users should wait ~15 minutes for tracking; third-party failures may prevent credit. | https://www.velooprewards.in/help-center/earning/watch-ads | Official | 2026-10-01 | Confirmed | Supports C4 third-party dependency design.
SRC-08 | Daily Check-In claim window 00:00-23:59 IST; missing a window may reset the streak. | https://www.velooprewards.in/help-center/earning/daily-rewards | Official | 2026-10-01 | Confirmed | Basis for IST reporting day.
SRC-09 | Referral reward is fixed; referred user may need to complete a first eligible activity and pass verification before reward approval. | https://www.velooprewards.in/help-center/safety/referral-rewards | Official | 2026-10-01 | Confirmed | Supports registered != converted distinction.
SRC-10 | Earning Session ('Mine & earn') lasts up to 1 h 30 min; simulated mechanic, not crypto mining or staking. | https://www.velooprewards.in/help-center/earning/mining-rewards | Official | 2026-10-01 | Confirmed | Conflicts with homepage footer link 'Staking' (SRC-14).
SRC-11 | Live help topics: watch ads, daily rewards, mine & earn, tap & earn, captcha, streaks, spin, missions & badges, levels, leaderboard, follow & earn, wallet, Gems Exchange, Swap Center, withdrawals, referrals, promo codes. Future (not live): Lucky Draw, Team Battle, Referral Milestones, Collect Cards, Surprise Rewards, Mystery Rewards. | https://www.velooprewards.in/help-center | Official | 2026-10-01 | Confirmed | A help page existing does not prove the feature is implemented or instrumented.
SRC-12 | Support email velooprewardsteam@gmail.com; business/legal veloop.ifratech@gmail.com; base Ramgarh, Jharkhand, India; reply 24-48 h (pages) vs 24-72 h (help-center header). | https://www.velooprewards.in/help-center | Official | 2026-10-01 | To Be Verified | Reply time stated two ways; homepage lists business@veloop.com; email lists velooprewardsofficial@gmail.com.
SRC-13 | Privacy policy: collects name, email, login credentials, device identifiers, IP, approximate location, Google login signals, reward/withdrawal records, cookies and ad events; shares with ad, offerwall, payout partners. | https://www.velooprewards.in/privacy-policy | Official | 2026-10-01 | Confirmed | Last updated May 18, 2026. Basis for governance proposal (deliverable 17).
SRC-14 | Homepage claims 'Registered Users 1 570 253+', 'Total Paid Out 1 500 470+', crypto-wallet payouts, sign-up with Google/Facebook/Apple/crypto wallet, 'Get Soon The App', footer link 'Staking', copyright 2025. | https://www.velooprewards.in/ | Official | 2026-10-01 | To Be Verified | NOT used as data. Conflicts with brief (VELOOP 'does not have the volume of production data') and with help pages (UPI/PayPal/gift cards; mining page says no staking).
SRC-15 | Missions and badges: badges may carry a reward or be recognition-only; rewards usually verified automatically after valid completion. | https://www.velooprewards.in/help-center/earning/missions-and-badges | Official | 2026-10-01 | Confirmed
SRC-16 | Gems Exchange Center: Gems convert to supported credits such as VEs at platform-set rates; exchanges may be reversed if invalid. | https://www.velooprewards.in/help-center/wallet/gems-exchange-center | Official | 2026-10-01 | Confirmed | Rates not published.
SRC-17 | Companion simulated datasets (Task_Activity, Rewards, Wallet, Withdrawals, Referrals, Feature_Events, Messy_Data, Tasks, Sessions). | data/simulated/ (scripts/generate_companion_data.py, seed 20260915) | Simulated | 2026-10-01 | Confirmed | Created by the analyst under section 28; labelled 'SIMULATED DATA — CREATED FOR ANALYTICAL TESTING'. Not VELOOP data.